## Slide 1
Title
certAIn Project Intelligence
AI-Powered Project Planning & Risk Forecasting App
Subtitle:
From deterministic planning to probability-based decision support.

## Slide 2
Problem
• Business question: can teams go from a short project brief to a defensible, risk-aware commitment in one planning session?
• Current state: teams commit to single-date plans without quantified uncertainty.
• Impact: delays appear late, mitigation is expensive, and stakeholder updates rely on intuition.

## Slide 3
Data and EDA
• Dataset: `1300` construction-task rows, `8` numeric features, `3` risk classes.
• Missing values: `0`; duplicate rows: `0`; duplicate task IDs: `0`.
• Class balance: `Low 50.8%`, `Medium 29.0%`, `High 20.2%`.
• Key insight: data is clean, but class separation is weak, so ML must remain advisory.

## Slide 4
Solution and Architecture
Flow:
1. User project description
2. LLM task generation (or mock fallback)
3. Schema validation (Pydantic)
4. DAG + critical path
5. Monte Carlo simulation
6. Metrics + scenarios + advisory ML + exports
Tech:
• Streamlit, Groq, Pydantic, NetworkX, NumPy/Pandas, Plotly, SQLite

## Slide 5
Live App Walkthrough
Show the 7 tabs:
• Executive Brief
• Task Plan
• Workflow
• Risk Dashboard
• ML Risk Scoring
• Scenario Lab
• History & Export

## Slide 6
Forecast Metrics
Explain:
• Mean completion time
• P50 (median outcome)
• P80 (recommended commitment date)
• Delay probability against selected deadline
Decision message:
Use P80 for realistic commitments under uncertainty.

## Slide 7
Model Comparison
• Baseline: `DummyClassifier` accuracy `0.5077`, macro F1 `0.2245`.
• Compared models: Logistic Regression, Random Forest, Extra Trees, HistGradientBoosting.
• Selected advisory model: `HistGradientBoosting`.
• Selection rule: highest cross-validated macro F1 (`0.3028`).

## Slide 8
Risk Drivers and Scenario Decision Support
• Critical-path frequency ranking identifies bottleneck tasks.
• Scenarios compared: baseline, aggressive deadline, increased capacity.
• Recommendation rule: choose the scenario with the lowest delay probability.
• Result: analytics becomes a concrete action recommendation, not only a chart.

## Slide 9
Product & Engineering Quality
• Input validation and graph checks
• Session persistence with SQLite
• Exportable CSV/JSON outputs
• Smoke test + unit test suite
• CI pipeline via GitHub Actions
• Dockerized local reproducibility

## Slide 10
Team Workflow and Validation
• Week 1: scope + architecture + base app
• Week 2: analytics engine + notebook
• Week 3: scenarios + persistence + test hardening
• Week 4: CI + rehearsal + final packaging
• Include DoR/DoD and ownership split between both teammates.
• Mention internal rehearsal findings and the target-user test template in `docs/mvp-test-synthesis.md`.

## Slide 11
Responsible AI (Right-Sized for Scope)
• No personal data required for this demo.
• User input transparency: generated plan is editable and reviewable.
• Risk note: LLM outputs can be imperfect; schema validation and manual review are required.
• ML note: classifier is advisory only because dataset signal is moderate.
Why included:
shows practical AI governance without over-scoping the project.

## Slide 12
Results, Limits, Next Steps
Results:
• Faster planning cycle
• Earlier risk visibility
• Better commitment quality
Current limits:
• Single-project scope
• No multi-user auth or PM-tool integrations
• No SQL-based training-data warehouse in this capstone snapshot
Next steps:
• Portfolio view
• Jira/Asana connectors
• Optional cloud deployment